## Sheet1
C14 Internal Audit Committee
NRNA ICC 2017 to 2019
Preliminary Draft Yearly Operation Plan to 31 December 2018
S.No | What | when | Who | Remarks
1 | Approve Terms of Reference | 2018-05-03 | All
2 | Official Announcement of Internal Audit Committee | 2018-05-07 | Chair
3 | Prepare group email / Viber Group | ASAP | Shamim / Mahendra
4 | Discuss and Finalise meeting to be conducted i.e. email, viber group, teleconference, SKYPE | ASAP | All
5 | Allocation of Tasks
5.1 | Review and prepare report on NRN Building Projects
5.2 | Review and prepare report on Lapark Projects
5.3 | Review and prepare report on Shankhamul Charity Projects
5.4 | Review of effectiveness of charity projects run by ICC /NCC in Nepal
5.5 | Prepare NCC brief Financial Reporting template
5.6 | Review of Audited FR (current) and Propose the following |  |  | It was a big issues during ICC Global conference and ICC members would like to improve it
Improve the presentation of FR
Timeline to prepare FR and audit so that Treasurer can send FR to all ICC member sand NCCs before
one month earlier next conference
Meeting with External auditor, Executive Director and Account Office at ICC Secretariat
6 | Prepare report of the above takes and submit with ICC Officer Bearers | 2018-12-31 | All
7 | Follow up and monitor |  | Chair / Co chair